## Blad1
Onderdeel | Beschrijving | Uren | 2018 | [14 empty] | 2019
|  |  | Sep |  | Okt |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan
Week
|  |  | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4
Audit 1 | Globale planning, templates, Business Case, Requirements | 15 | [19 empty] | Gepland in week | bar: Week 38
Oplevering | HTML/CSS website ieder teamlid | 15 | [19 empty] | Niet gepland in week | bar: Week 39
Coaching |  | 2.5 | [19 empty] | Vakantie indien niet anders aangegeven | bar: Week 39
Workshop | Git en Markdown | 7.5 | bar: Week 40
Coaching |  | 2.5 | bar: Week 40
Workshop | JavaScript en jQuery | 7.5 | bar: Week 41
Coaching |  | 2.5 | bar: Week 41
Workshop | JavaScript, JSON en AJAX | 7.5 | bar: Week 42
Audit 2 |  | 15 | bar: Week 42
Coaching |  | 2.5 | bar: Week 42
Oplevering | Website HTML/CSS en JavaScript met Documentatie in Gitlab | 30 | bar: Week 42
Coaching |  | 2.5 | bar: Week 44
Oplevering | Procescheck | 15 | bar: Week 44
Coaching |  | 2.5 | bar: Week 46
Coaching |  | 2.5 | bar: Week 47
Workshop | Backend in Node.js | 7.5 | bar: Week 47
Coaching |  | 2.5 | bar: Week 48
Workshop | JavaScript EHBJ | 7.5 | bar: Week 48
Coaching |  | 2.5 | bar: Week 49
Audit 3 |  | 15 | bar: Week 49
Oplevering | Concept eindproduct Website met jQuery, Node.js en MySQL | 25 | bar: Week 49
Coaching |  | 2.5 | bar: Week 50
Workshop | Testing | 7.5 | bar: Week 50
Coaching |  | 2.5 | bar: Week 51
Coaching |  | 2.5 | bar: Week 2
Audit 4 |  | 15 | bar: Week 2
Oplevering | Reflectieverslag | 15 | bar: Week 2
Oplevering | Productpresentatie | 7.5 | bar: Week 3
Oplevering | Eindproduct HTML, CSS, Javascript, jQuery, Node.js, MySQL DB | 40 | bar: Week 3
Documentatie Markdown in GitLab, Gebruikershandleiding + testverslag | bar: Week 3
Toets | Methode en techniekentoets | 7.5 | bar: Week 4
Kick-out |  | 10 | bar: Week 4
[7 empty] | Herfstvakantie |  |  | Tentamenweek | [5 empty] | Kerstvakantie